## Instructions
Activity 01 — Launch the Orion Continuous Improvement System
Orion Precision Electronics (OPE)
Mapping | A1, A2, K1
Objective | Create governance, coaching and visible management for the improvement effort.
Scenario | Orion's SMT line has competing priorities, informal escalation and no shared definition of success.
Deliverable | CI charter, role map, coaching cadence and daily/weekly review board
Acceptance check | A reviewer can identify the gap, target, measures, owners, cadence and coaching approach without asking for missing definitions.
Learner note | Follow the detailed procedure in README.md or the Learner Guide. Blue cells contain examples or formulas; complete the remaining evidence.

## Charter
Improvement Charter
Field | Agreed statement
Problem | SMT bridge defects increased from 1.8% to 4.6% during the product ramp-up
Scope | Released kit through inspected board ready for electrical test
90-day goal | Reduce bridge defects to ≤1.5% while keeping cycle time ≤48 s/board
Guardrail | No increase in insufficient-solder defects or first-piece release time

## Measures
Measure System
Measure | Baseline | Target | Unit | Owner | Frequency
Bridge defect rate | 0.046 | 0.015 | % lots | Quality Engineer | Daily
First-pass yield | 0.932 | 0.975 | % boards | Process Owner | Daily
Cycle time | 51.4 | 48 | seconds/board | Production Lead | Shift

## Roles
Team Role Map
Role | Accountability | Named owner | Decision boundary
Sponsor | Approve priority and remove barriers | Operations Director | Funding and escalation
Process owner | Own process performance and sustainment | SMT Manager | Standard work and controls
Facilitator | Maintain method and balanced participation | CI Lead | Analysis cadence

## Governance
Governance Cadence
Cadence | Purpose | Evidence | Owner | Escalation trigger
Daily | Review defect and stop signals | Shift board | Shift Lead | >3 bridge defects/lot
Weekly | Review actions and learning | Action register | CI Lead | Overdue high-risk action
Monthly | Confirm benefits and controls | KPI and audit | Process Owner | Target missed 2 periods