## Instructions
Activity 06 — Rate Risk, Plan Actions and Re-score
Orion Precision Electronics (OPE)
Mapping | A5, A6, K3
Objective | Prioritise PFMEA actions using severity-first judgement, RPN context and verified re-rating.
Scenario | Several Orion rows have similar RPNs but different customer and safety consequences.
Deliverable | Rated PFMEA with RPN formulas, internal action-priority guardrail, owners, due dates and post-action scores
Acceptance check | All RPN formulas are correct, severe risks remain visible, actions have ownership/evidence, and post-action ratings match the control change.
Learner note | Follow the detailed procedure in README.md or the Learner Guide. Blue cells contain examples or formulas; complete the remaining evidence.

## Scope
PFMEA Scope and Team
Field | Decision / evidence
Purpose | Prevent SMT solder defects during Orion product ramp
Boundary | Kit release through inspection release
Team | Process, production, quality, maintenance and operators
Review triggers | Change, capability signal, incident, complaint or RCA learning

## PFMEA
Orion Process FMEA
RPN = Severity × Occurrence × Detection; higher D means weaker detection
ID | Process step | Function / requirement | Failure mode | Effect | S | Cause | O | Prevention control | Detection control | D | RPN | Action | Owner | Due | New S | New O | New D | New RPN
P-01 | Print paste | Deposit paste within volume specification | Excess paste | Bridge causes intermittent signal / customer return | 8 | Stencil aperture partly blocked | 6 | Fixed cleaning interval | AOI after reflow | 5 |  | Condition-based cleaning trigger | Process Engineer | 2026-09-15 | 8 | 3 | 4
P-02 | Place component | Place component within alignment tolerance | Misaligned component | Open or weak joint at test | 7 | Feeder indexing wear | 4 | Preventive maintenance | AOI alignment check | 3 |  | Add feeder-life alert | Maintenance Lead | 2026-09-20 | 7 | 2 | 3
P-03 | Reflow | Heat joints within validated profile | Incomplete wetting | Insufficient solder / early-life failure | 8 | Profile drifts after product change | 3 | Recipe approval | First-piece test | 4 |  | Interlock recipe to product ID | Controls Engineer | 2026-09-25 | 8 | 2 | 2

## Rating Guides
Internal S/O/D Learning Guide
Illustrative course guide only; use the organisation's approved scale in real work
Score | Severity guide | Occurrence guide | Detection guide
1 | Minor / local | Rare | Almost certain detection
2 | Minor / local | Rare | Almost certain detection
3 | Minor / local | Rare | Almost certain detection
4 | Moderate | Occasional | Moderate detection
5 | Moderate | Occasional | Moderate detection
6 | Moderate | Occasional | Moderate detection
7 | Major / customer / safety | Frequent | Weak / unlikely detection
8 | Major / customer / safety | Frequent | Weak / unlikely detection
9 | Major / customer / safety | Frequent | Weak / unlikely detection
10 | Major / customer / safety | Frequent | Weak / unlikely detection

## Risk Review
Severity-First Risk Review
PFMEA ID | S | O | D | RPN | Why action is / is not required
P-01 |  |  |  |  | Customer return and weak prevention control

## Actions
Action Register
PFMEA ID | Action | Hierarchy | Owner | Due | Implementation evidence | Effectiveness evidence | Status
P-01 | Condition-based stencil-cleaning trigger | Prevention | Process Engineer | 2026-09-15 | Approved program + WI | Pilot comparison | Planned

## Re-score
Post-Action Re-score
PFMEA ID | Old RPN | Verified change | New S | New O | New D | New RPN | Residual decision
P-01 |  | Trigger implemented and pilot effective |  |  |  |  | Monitor in Control Plan