## Instructions
Activity 08 — Pilot, Direct and Coach the Change
Orion Precision Electronics (OPE)
Mapping | A7, A8, K2
Objective | Plan a controlled pilot and direct team implementation with coaching and change safeguards.
Scenario | Orion will pilot an automated stencil-cleaning trigger and first-piece verification on Printer P2.
Deliverable | Pilot charter, before/after measurement plan, risk guardrails, training and coaching checklist
Acceptance check | The pilot is measurable, contained and reversible; the change has approvals, training and a documented scale/revise/stop rule.
Learner note | Follow the detailed procedure in README.md or the Learner Guide. Blue cells contain examples or formulas; complete the remaining evidence.

## Charter
Pilot Charter
Field | Definition | Owner
Hypothesis | A print-volume trigger prompts cleaning before aperture blockage creates bridges | Process Engineer
Scope | Printer P2, two products, both shifts, two weeks | SMT Manager
Decision | Scale if ≥50% bridge reduction with no guardrail breach | Process Owner

## Measures
Pilot Measures
Type | Measure | Baseline | Target | Definition | Frequency
Outcome | Bridge defect rate | 0.046 | 0.023 | Bridge lots / inspected lots | Daily
Leading | Cleaning trigger compliance | 0 | 0.95 | Completed triggers / generated triggers | Shift
Guardrail | Cycle time | 51.4 | 52 | Average seconds/board | Daily

## Design
Pilot Design and Reaction
Element | Decision | Reason / safeguard
Products | SC-100 and SC-200 | Representative aperture patterns
Stop rule | Stop if defects exceed 6% or safety interlock is bypassed | Contain risk
Rollback | Restore validated fixed interval and contain suspect lots | Reversible change

## Change Control
Temporary Change Control
Change | Approval | Document | Training | Status
Condition-based cleaning trigger | Engineering + Quality | Temporary WI-17 | Operators and shift leads | Approved

## Coaching
Coaching Observation
Stage | Coach behaviour | Learner evidence | Result / feedback
Explain | Connect trigger to defect mechanism | Operator explains why
Demonstrate | Show trigger response and record | Operator observes full cycle
Practice | Operator responds to simulated trigger | Correct action without prompt
Observe | Watch normal production response | Adherence record
Feedback | Reinforce and correct specifically | Operator confirms next action

## Decision
Scale / Revise / Stop
Outcome | Guardrails | Adoption | Decision | Rationale | Approval
63% bridge reduction | No cycle-time breach | 96% trigger compliance | Scale | Meets rule across both shifts | Process Owner