## Instructions
Activity 08 — Pilot, Direct and Coach the Change
Orion Precision Electronics (OPE)
Mapping | A7, A8, K2
Objective | Plan a controlled pilot and direct team implementation with coaching and change safeguards.
Scenario | Orion will pilot an automated stencil-cleaning trigger and first-piece verification on Printer P2.
Deliverable | Pilot charter, before/after measurement plan, risk guardrails, training and coaching checklist
Acceptance check | The pilot is measurable, contained and reversible; the change has approvals, training and a documented scale/revise/stop rule.
Learner note | Follow the detailed procedure in README.md or the Learner Guide. Blue cells contain examples or formulas; complete the remaining evidence.

## Charter
Pilot Charter
Field | Definition | Owner
Hypothesis
Scope
Decision

## Measures
Pilot Measures
Type | Measure | Baseline | Target | Definition | Frequency
Outcome | Bridge defect rate |  |  |  | Daily
Leading | Cleaning trigger compliance |  |  |  | Shift
Guardrail | Cycle time |  |  |  | Daily

## Design
Pilot Design and Reaction
Element | Decision | Reason / safeguard
Products
Stop rule
Rollback

## Change Control
Temporary Change Control
Change | Approval | Document | Training | Status

## Coaching
Coaching Observation
Stage | Coach behaviour | Learner evidence | Result / feedback
Explain
Demonstrate
Practice
Observe
Feedback

## Decision
Scale / Revise / Stop
Outcome | Guardrails | Adoption | Decision | Rationale | Approval